## Dashboard
Full Stack + GenAI — Roadmap Progress Tracker
Track your journey from zero to Full Stack + GenAI engineer
Overall Progress
Phase | Weeks | Objective | Project | Total | Done | In Prog | Blocked | % Done | Progress Bar | Current Status
Phase 1 — Foundation | 1–3 | Learn JS basics + build first REST API | —
Phase 2 — Backend | 4–6 | Build real backend with DB + Auth | TODO App (Backend)
Phase 3 — Full Stack | 7–9 | Build complete UI + backend application | TODO App (Full Stack)
Phase 4 — GenAI | 10–12 | Add LLM, embeddings, RAG pipeline | TODO App + AI
Phase 5 — Interview Project | 13–16 | Build Document QnA Chatbot from scratch | Document QnA Chatbot
Phase 6 — Deployment + Jobs | — | Deploy publicly + Resume + Apply | Live on Vercel + Render
TOTAL
STATUS LEGEND
Not Started | In Progress | Done | Blocked | Skipped

## Task Tracker
Task Tracker — Full Stack + GenAI Roadmap
# | Phase | Wks | Category | Task | Description | Priority | Status | Start Date | Target Date | Done Date | Hrs | Notes / Learnings
1 | Phase 1 — Foundation | 1–3 | Setup | Install Node.js & VS Code | Install Node.js LTS, VS Code, ESLint + Prettier extensions, configure workspace | Medium | Not Started
2 | Phase 1 — Foundation | 1–3 | JS Basics | Variables & Data Types | var/let/const, string/number/boolean/null/undefined, typeof, type coercion | Medium | Not Started
3 | Phase 1 — Foundation | 1–3 | JS Basics | Control Flow | if/else, switch, ternary, for/while/do-while, break/continue | Medium | Not Started
4 | Phase 1 — Foundation | 1–3 | JS Basics | Arrays & Methods | map, filter, reduce, find, forEach, some, every, flat, spread operator | Medium | Not Started
5 | Phase 1 — Foundation | 1–3 | JS Basics | Objects & Prototypes | Literals, destructuring, optional chaining (?.), nullish coalescing (??), spread | Medium | Not Started
6 | Phase 1 — Foundation | 1–3 | JS Basics | Functions & Closures | Arrow functions, default params, rest params, IIFE, closures, HOFs | Medium | Not Started
7 | Phase 1 — Foundation | 1–3 | Async JS | Callbacks & Promises | Callback hell, Promise chain (.then/.catch), Promise.all, Promise.race | Medium | Not Started
8 | Phase 1 — Foundation | 1–3 | Async JS | async / await | async functions, await keyword, try/catch error handling, parallel await | Medium | Not Started
9 | Phase 1 — Foundation | 1–3 | ES6+ | Modules & Modern Syntax | import/export, template literals, destructuring assignment, optional chaining | Medium | Not Started
10 | Phase 1 — Foundation | 1–3 | Express.js | Project Setup | npm init, install express cors body-parser, nodemon, folder structure (routes/controllers) | Medium | Not Started
11 | Phase 1 — Foundation | 1–3 | Express.js | GET Endpoints | app.get(), route params (:id), query strings (?key=val), send JSON responses | Medium | Not Started
12 | Phase 1 — Foundation | 1–3 | Express.js | POST Endpoints | app.post(), express.json() middleware, body parsing, create resource flow | Medium | Not Started
13 | Phase 1 — Foundation | 1–3 | Express.js | Middleware & Errors | Custom middleware chain, cors(), morgan, 404 handler, global error middleware | Medium | Not Started
14 | Phase 1 — Foundation | 1–3 | Testing | Postman Collections | Create workspace, collection, test GET/POST/PUT/DELETE, environment vars, export | Medium | Not Started
15 | Phase 1 — Foundation | 1–3 | Testing | REST Principles | HTTP methods, status codes (200/201/400/401/404/500), idempotency, RESTful naming | Medium | Not Started
1 | Phase 2 — Backend | 4–6 | PostgreSQL | Install & Configure | Install PostgreSQL, create DB user + database, connect via psql or pgAdmin | Medium | Not Started
2 | Phase 2 — Backend | 4–6 | PostgreSQL | SQL Fundamentals | CREATE TABLE, INSERT, SELECT, WHERE, JOIN (INNER/LEFT), ORDER BY, LIMIT | Medium | Not Started
3 | Phase 2 — Backend | 4–6 | PostgreSQL | DB Schema Design | Design users & tasks tables, primary keys, foreign keys, constraints, indexes | Medium | Not Started
4 | Phase 2 — Backend | 4–6 | Prisma ORM | Setup & Configure | npm install prisma @prisma/client, prisma init, configure DATABASE_URL in .env | Medium | Not Started
5 | Phase 2 — Backend | 4–6 | Prisma ORM | Schema Definition | Define User and Task models, @relation, @unique, @default, DateTime fields | Medium | Not Started
6 | Phase 2 — Backend | 4–6 | Prisma ORM | Migrations | prisma migrate dev --name init, inspect generated SQL, prisma studio | Medium | Not Started
7 | Phase 2 — Backend | 4–6 | Prisma ORM | Prisma Client CRUD | findMany, findUnique, create, update, delete, upsert with Prisma Client | Medium | Not Started
8 | Phase 2 — Backend | 4–6 | Auth | Password Hashing (bcrypt) | npm install bcryptjs, hash on register (saltRounds=10), compare on login | Medium | Not Started
9 | Phase 2 — Backend | 4–6 | Auth | JWT Token Generation | npm install jsonwebtoken, sign with secret+expiry, verify, decode payload | Medium | Not Started
10 | Phase 2 — Backend | 4–6 | Auth | Auth Middleware | Extract Bearer token from header, verify JWT, attach req.user, protect routes | Medium | Not Started
11 | Phase 2 — Backend | 4–6 | Auth | Register Endpoint | POST /auth/register — validate input, check duplicate email, hash, save to DB | Medium | Not Started
12 | Phase 2 — Backend | 4–6 | Auth | Login Endpoint | POST /auth/login — find user, compare hash, sign + return JWT + user data | Medium | Not Started
13 | Phase 2 — Backend | 4–6 | CRUD API | Task Endpoints | GET/POST/PUT/DELETE /tasks — all protected, user-scoped, full CRUD with DB | Medium | Not Started
14 | Phase 2 — Backend | 4–6 | CRUD API | Input Validation | Validate required fields, types, lengths; return 400 with descriptive errors | Medium | Not Started
15 | Phase 2 — Backend | 4–6 | CRUD API | Integration Test | Postman: register → login → create/read/update/delete tasks → verify auth guards | Medium | Not Started
1 | Phase 3 — Full Stack | 7–9 | React | Project Setup (Vite) | npm create vite@latest, choose React template, clean boilerplate, folder structure | Medium | Not Started
2 | Phase 3 — Full Stack | 7–9 | React | Components & Props | Functional components, prop types, children, composition, reusable UI components | Medium | Not Started
3 | Phase 3 — Full Stack | 7–9 | React | useState Hook | Form state, counter, toggle, controlled inputs, derived state patterns | Medium | Not Started
4 | Phase 3 — Full Stack | 7–9 | React | useEffect Hook | Fetch on mount, cleanup function, dependency array, avoid infinite re-renders | Medium | Not Started
5 | Phase 3 — Full Stack | 7–9 | React | Custom Hooks | useAuth (token/user state), useTasks (fetch + CRUD), useForm (generic handler) | Medium | Not Started
6 | Phase 3 — Full Stack | 7–9 | Tailwind CSS | Setup & Config | npm install tailwindcss, tailwind.config.js, JIT mode, purge paths, base styles | Medium | Not Started
7 | Phase 3 — Full Stack | 7–9 | Tailwind CSS | Layout & Responsive | Flexbox, grid, responsive breakpoints (sm/md/lg/xl), sidebar + main layout | Medium | Not Started
8 | Phase 3 — Full Stack | 7–9 | Tailwind CSS | Theming & Reuse | Custom colors in config, dark mode, @apply for repeated component styles | Medium | Not Started
9 | Phase 3 — Full Stack | 7–9 | Axios | Instance & Interceptors | Create Axios instance with baseURL, request interceptor to attach JWT header | Medium | Not Started
10 | Phase 3 — Full Stack | 7–9 | Axios | API Service Layer | auth.js and tasks.js service files — centralise all API calls, handle errors | Medium | Not Started
11 | Phase 3 — Full Stack | 7–9 | Auth UI | Login & Register Forms | Controlled forms, client-side validation, show API errors inline, loading button | Medium | Not Started
12 | Phase 3 — Full Stack | 7–9 | Auth UI | Token Storage | Store JWT in localStorage, parse on app load, clear on logout, expiry handling | Medium | Not Started
13 | Phase 3 — Full Stack | 7–9 | Auth UI | Protected Routes | React Router v6, <RequireAuth> wrapper, redirect to /login if no valid token | Medium | Not Started
14 | Phase 3 — Full Stack | 7–9 | Task UI | Task List | Fetch & render tasks, loading skeleton, empty state illustration, task count | Medium | Not Started
15 | Phase 3 — Full Stack | 7–9 | Task UI | Task CRUD UI | Add task form, inline edit mode, delete confirm dialog, complete toggle checkbox | Medium | Not Started
16 | Phase 3 — Full Stack | 7–9 | UX | Loading & Error States | Spinner/skeleton during fetch, toast notifications (react-hot-toast), retry button | Medium | Not Started
17 | Phase 3 — Full Stack | 7–9 | UX | End-to-End Integration Test | Register → Login → CRUD tasks → Logout → all UI states verified manually | Medium | Not Started
1 | Phase 4 — GenAI | 10–12 | Ollama | Install & Start Service | brew install ollama, ollama serve, verify running on localhost:11434 | Medium | Not Started
2 | Phase 4 — GenAI | 10–12 | Ollama | Pull LLM Models | ollama pull llama3, ollama pull mistral, compare output quality | Medium | Not Started
3 | Phase 4 — GenAI | 10–12 | Ollama | Test LLM via Terminal | ollama run llama3, chat, try different prompts, understand context window | Medium | Not Started
4 | Phase 4 — GenAI | 10–12 | Ollama | Ollama REST API | POST /api/generate, stream:false, stream:true — call from Node.js with fetch | Medium | Not Started
5 | Phase 4 — GenAI | 10–12 | Embeddings | Concept & Theory | What are embeddings, vector space, cosine similarity, why they matter for RAG | Medium | Not Started
6 | Phase 4 — GenAI | 10–12 | Embeddings | Pull Embedding Model | ollama pull nomic-embed-text, test POST /api/embeddings, inspect vector dimensions | Medium | Not Started
7 | Phase 4 — GenAI | 10–12 | Embeddings | Similarity Search Concept | Compute cosine similarity manually in JS, understand k-nearest-neighbor | Medium | Not Started
8 | Phase 4 — GenAI | 10–12 | LangChain JS | Setup | npm install langchain @langchain/community @langchain/ollama | Medium | Not Started
9 | Phase 4 — GenAI | 10–12 | LangChain JS | Simple Chain | PromptTemplate → OllamaLLM → StringOutputParser — test with simple questions | Medium | Not Started
10 | Phase 4 — GenAI | 10–12 | FAISS | Setup & Basic Ops | npm install faiss-node (or via @langchain/community), create store, basic test | Medium | Not Started
11 | Phase 4 — GenAI | 10–12 | FAISS | Vector Store CRUD | addDocuments, similaritySearch(query, k), saveLocal, loadFromLocal | Medium | Not Started
12 | Phase 4 — GenAI | 10–12 | RAG | Build RAG Chain | Query → FAISS similarity search → format context → Ollama LLM → answer | Medium | Not Started
13 | Phase 4 — GenAI | 10–12 | RAG | End-to-End Test | Feed 5+ documents, ask 10 questions, verify retrieved context is relevant | Medium | Not Started
14 | Phase 4 — GenAI | 10–12 | AI Features | NL Task Input | Parse natural language ("remind me Friday") via LLM → structured task → DB | Medium | Not Started
15 | Phase 4 — GenAI | 10–12 | AI Features | AI Task Suggestions | Based on existing tasks, ask LLM for next recommended actions with context | Medium | Not Started
16 | Phase 4 — GenAI | 10–12 | AI Features | Full Integration Test | Test NL input + AI suggestions in TODO app (React + Express + Ollama + FAISS) | Medium | Not Started
1 | Phase 5 — Interview Project | 13–16 | Planning | Architecture Design | Draw full system diagram, define all API endpoints, data flow, tech decisions | Medium | Not Started
2 | Phase 5 — Interview Project | 13–16 | Backend | Express.js Setup | New project, folder structure (routes/controllers/services), env vars, nodemon | Medium | Not Started
3 | Phase 5 — Interview Project | 13–16 | Backend | File Upload (Multer) | npm install multer, diskStorage config, MIME type + size validation, /uploads dir | Medium | Not Started
4 | Phase 5 — Interview Project | 13–16 | Backend | PDF Parser | LangChain PDFLoader or pdf-parse — extract raw text from uploaded PDF | Medium | Not Started
5 | Phase 5 — Interview Project | 13–16 | Backend | TXT Parser | fs.readFile for plain text, normalize whitespace, handle encoding (UTF-8) | Medium | Not Started
6 | Phase 5 — Interview Project | 13–16 | LangChain | Text Chunking | RecursiveCharacterTextSplitter, chunkSize:500, chunkOverlap:50, inspect chunks | Medium | Not Started
7 | Phase 5 — Interview Project | 13–16 | LangChain | Embed Chunks | OllamaEmbeddings with nomic-embed-text, embed all chunks, inspect vector shape | Medium | Not Started
8 | Phase 5 — Interview Project | 13–16 | FAISS | Build Vector Store | FaissStore.fromDocuments(), save per documentId, load on query request | Medium | Not Started
9 | Phase 5 — Interview Project | 13–16 | Backend | Retrieval Endpoint | POST /ask — load FAISS for doc, similaritySearch top 5, return chunks + metadata | Medium | Not Started
10 | Phase 5 — Interview Project | 13–16 | LangChain | RAG Pipeline | RetrievalQAChain or custom: retrieve → format context → Ollama → response | Medium | Not Started
11 | Phase 5 — Interview Project | 13–16 | Backend | Streaming Response | Stream Ollama response via Server-Sent Events (res.write) or chunked transfer | Medium | Not Started
12 | Phase 5 — Interview Project | 13–16 | Frontend | React + Tailwind Setup | Vite + React, install Tailwind + Axios, folder structure, Axios base instance | Medium | Not Started
13 | Phase 5 — Interview Project | 13–16 | Frontend | Upload Panel | Drag-and-drop or click-to-upload, file type badge, upload progress indicator | Medium | Not Started
14 | Phase 5 — Interview Project | 13–16 | Frontend | Chat UI | Message thread (user/bot bubbles), auto-scroll to bottom, timestamps, avatars | Medium | Not Started
15 | Phase 5 — Interview Project | 13–16 | Frontend | Streaming in UI | Handle chunked tokens as they arrive, typewriter effect, stop generation button | Medium | Not Started
16 | Phase 5 — Interview Project | 13–16 | Frontend | Loading & Error States | Skeleton loaders, error toast, retry button, empty state with upload prompt | Medium | Not Started
17 | Phase 5 — Interview Project | 13–16 | Quality | Full Local Test | Upload 3+ docs, ask 10+ questions per doc, verify answer accuracy and relevance | Medium | Not Started
18 | Phase 5 — Interview Project | 13–16 | Quality | Write README | Architecture diagram, setup instructions, screenshots, demo GIF, tech stack badges | Medium | Not Started
1 | Phase 6 — Deployment + Jobs | — | Deployment | Vercel Account Setup | Sign up Vercel, install CLI (npm i -g vercel), link GitHub account | Medium | Not Started
2 | Phase 6 — Deployment + Jobs | — | Deployment | Frontend Env Vars | Set VITE_API_URL to Render backend URL in Vercel Environment Variables settings | Medium | Not Started
3 | Phase 6 — Deployment + Jobs | — | Deployment | Deploy Frontend to Vercel | vercel --prod, verify build output, test on *.vercel.app live URL | Medium | Not Started
4 | Phase 6 — Deployment + Jobs | — | Deployment | Render Account Setup | Sign up Render, New Web Service, connect GitHub repo, set runtime: Node | Medium | Not Started
5 | Phase 6 — Deployment + Jobs | — | Deployment | Backend Env Vars | Set DATABASE_URL, JWT_SECRET, CORS_ORIGIN, NODE_ENV=production on Render | Medium | Not Started
6 | Phase 6 — Deployment + Jobs | — | Deployment | Deploy Backend to Render | Set build cmd: npm install, start cmd: node server.js, enable auto-deploy | Medium | Not Started
7 | Phase 6 — Deployment + Jobs | — | Deployment | Cloud Database (Neon) | Create Neon or Supabase project, copy connection string, set on Render env | Medium | Not Started
8 | Phase 6 — Deployment + Jobs | — | Deployment | Migrate Schema to Cloud | DATABASE_URL=<neon_url> npx prisma migrate deploy — verify tables in cloud | Medium | Not Started
9 | Phase 6 — Deployment + Jobs | — | Deployment | Smoke Test Live App | Login, CRUD tasks, upload document, ask question — all on production URL | Medium | Not Started
10 | Phase 6 — Deployment + Jobs | — | Portfolio | Public URL + Screenshots | Copy live URL, take screenshots of key flows, record 60-sec demo GIF | Medium | Not Started
11 | Phase 6 — Deployment + Jobs | — | Portfolio | Update README | Add live demo badge, screenshots, architecture diagram, local setup guide | Medium | Not Started
12 | Phase 6 — Deployment + Jobs | — | Portfolio | GitHub Cleanup | Pin 2 repos, add descriptions, clean commits, remove test files + console.logs | Medium | Not Started
13 | Phase 6 — Deployment + Jobs | — | Job Prep | Resume Bullets | 2-3 bullets per project: action verb + tech stack + measurable outcome/metric | Medium | Not Started
14 | Phase 6 — Deployment + Jobs | — | Job Prep | LinkedIn Profile Update | Update headline + about section, add projects, post publicly about project | Medium | Not Started
15 | Phase 6 — Deployment + Jobs | — | Job Prep | Apply Round 1 | Apply to 10 jobs on LinkedIn + Naukri with tailored resume + cover note | Medium | Not Started
16 | Phase 6 — Deployment + Jobs | — | Job Prep | Apply Round 2 | 10 more applications, ask connections for referrals, follow up after 1 week | Medium | Not Started
17 | Phase 6 — Deployment + Jobs | — | Interview Prep | Mock: TODO App System | Explain architecture, DB schema design, auth flow, Prisma decisions, trade-offs | Medium | Not Started
18 | Phase 6 — Deployment + Jobs | — | Interview Prep | Mock: Doc QnA AI Flow | Explain RAG pipeline step-by-step, embedding strategy, why FAISS, LangChain role | Medium | Not Started
19 | Phase 6 — Deployment + Jobs | — | Interview Prep | DSA Prep | Arrays, strings, hashmaps — solve 20 easy LeetCode problems, time yourself | Medium | Not Started
20 | Phase 6 — Deployment + Jobs | — | Interview Prep | HR Questions | Tell me about yourself, strengths, why this role, salary expectations, notice period | Medium | Not Started

## Weekly Log
Weekly Log — Track What You Do Each Week
Wk | Dates | Phase | Weekly Goal | What I Completed | What I'm Stuck On | Key Learning | Mon | Tue | Wed | Thu | Fri | Sat | Total Hrs | Status | Notes
W1 | 14 Jul – 20 Jul | Phase 1 — Foundation | [11 empty] | Not Started
W2 | 21 Jul – 27 Jul | Phase 1 — Foundation | [11 empty] | Not Started
W3 | 28 Jul – 3 Aug | Phase 1 — Foundation | [11 empty] | Not Started
W4 | 4 Aug – 10 Aug | Phase 2 — Backend | [11 empty] | Not Started
W5 | 11 Aug – 17 Aug | Phase 2 — Backend | [11 empty] | Not Started
W6 | 18 Aug – 24 Aug | Phase 2 — Backend | [11 empty] | Not Started
W7 | 25 Aug – 31 Aug | Phase 3 — Full Stack | [11 empty] | Not Started
W8 | 1 Sep – 7 Sep | Phase 3 — Full Stack | [11 empty] | Not Started
W9 | 8 Sep – 14 Sep | Phase 3 — Full Stack | [11 empty] | Not Started
W10 | 15 Sep – 21 Sep | Phase 4 — GenAI | [11 empty] | Not Started
W11 | 22 Sep – 28 Sep | Phase 4 — GenAI | [11 empty] | Not Started
W12 | 29 Sep – 5 Oct | Phase 4 — GenAI | [11 empty] | Not Started
W13 | 6 Oct – 12 Oct | Phase 5 — Interview Project | [11 empty] | Not Started
W14 | 13 Oct – 19 Oct | Phase 5 — Interview Project | [11 empty] | Not Started
W15 | 20 Oct – 26 Oct | Phase 5 — Interview Project | [11 empty] | Not Started
W16 | 27 Oct – 2 Nov | Phase 5 — Interview Project | [11 empty] | Not Started
TOTAL HOURS LOGGED

## Projects
Project Tracker — TODO App & Document QnA Chatbot
| PROJECT 1 — TODO App (Full Stack + AI) |  |  | PROJECT 2 — Document QnA Chatbot
| Feature / Milestone | Status | Notes | Feature / Milestone | Status | Notes
| Backend: Node.js + Express API |  |  | Express.js backend project setup
| PostgreSQL DB with Prisma ORM |  |  | File upload (Multer — PDF/TXT)
| JWT Authentication (register + login) |  |  | PDF/TXT parsing
| Full CRUD: Tasks (protected routes) |  |  | Text chunking (LangChain splitter)
| Frontend: React + Vite |  |  | Embeddings (nomic-embed-text)
| Tailwind CSS styling |  |  | FAISS vector store per document
| Axios API integration |  |  | RAG retrieval chain (LangChain JS)
| Login / Register UI |  |  | Ollama LLM response generation
| Protected routes (React Router v6) |  |  | Streaming API response (SSE)
| Task list + CRUD UI |  |  | React chat UI (bubble thread)
| AI: Ollama LLM integration |  |  | File upload panel (drag & drop)
| FAISS vector store |  |  | Streaming typewriter effect in UI
| LangChain RAG pipeline |  |  | Loading + error states
| Natural language task input |  |  | README with architecture diagram
| AI smart suggestions feature |  |  | Full local end-to-end test

## Interview Prep
Interview Prep — Topics, Practice Questions & Confidence Tracker
# | Category | Topic | Confidence (1-5) | Practice Question 1 | Practice Question 2 | Mock Score (1-10) | Notes / Answers
1 | System Design | Full Stack Architecture |  | Walk me through the architecture of your TODO app — frontend to DB. | Why did you choose PostgreSQL over MongoDB for this project?
2 | System Design | Database Design |  | Explain the schema — tables, relations, constraints you used. | What indexes did you add and why?
3 | Backend | Express.js Middleware |  | What is middleware? How does the middleware chain work? | How did you handle authentication in your Express app?
4 | Backend | JWT Authentication |  | Explain the full JWT auth flow — register, login, protected route. | What are the trade-offs between JWT and session-based auth?
5 | Backend | Prisma ORM |  | What is an ORM? Why did you use Prisma over raw SQL? | How does Prisma migration work?
6 | Frontend | React Hooks |  | Explain useState and useEffect with a real example from your project. | What is a custom hook and why did you create one?
7 | Frontend | State Management |  | How do you manage auth state across your React app? | When would you use Context API vs Redux?
8 | Frontend | API Integration |  | How does your React app communicate with the backend? | How did you handle token expiry on the frontend?
9 | GenAI | What is RAG? |  | Explain Retrieval-Augmented Generation in simple terms. | Why is RAG better than just prompting the LLM directly?
10 | GenAI | Embeddings |  | What are text embeddings? How do you generate them in your project? | What is cosine similarity and how is it used in your system?
11 | GenAI | FAISS |  | What is FAISS? Why did you choose it over other vector stores? | How does similaritySearch work in your Document QnA app?
12 | GenAI | LangChain JS |  | What role does LangChain play in your system? | Explain the retrieval chain you built step by step.
13 | GenAI | Ollama |  | What is Ollama and why did you run the LLM locally? | How would you replace Ollama with a cloud LLM like OpenAI?
14 | Deployment | Vercel + Render |  | Explain your deployment architecture — what runs where? | How do frontend and backend communicate in production?
15 | Deployment | Cloud Database |  | Why did you switch from local PostgreSQL to Neon/Supabase? | How did you handle the migration to the cloud DB?
16 | Soft Skills | About the Project |  | Tell me about your Document QnA project — what does it do? | What was the hardest part of building it and how did you solve it?
17 | Soft Skills | Tech Decisions |  | Why did you choose Node.js over Python for your backend? | What would you do differently if you rebuilt this project?
18 | Soft Skills | Learning Journey |  | How did you learn all of this? What resources did you use? | Where do you see yourself in 2 years as a Full Stack + AI engineer?
19 | DSA | Arrays & Strings |  | Find the two numbers in an array that sum to a target. | Reverse words in a sentence without using split().
20 | DSA | Hash Maps |  | Find the first non-repeating character in a string. | Group anagrams from an array of strings.